## Slide 1
Alpha Manufacturing Group
ERP Transformation
Executive Presentation
Business-led cloud ERP replacement strategy to protect operations, strengthen data governance and improve margin transparency.
Prepared for AMG Executive Team
Take-home case submission
Legacy
ERP
Modern
Cloud ERP
Margin
Visibility
Notes: Open by framing this as a business-control transformation rather than simply a software replacement.

## Slide 2
Executive recommendation
A controlled core ERP release, not an uncontrolled “replace everything” program.
02
RECOMMENDATION
Proceed with a business-led, fit-to-standard ERP program with formal readiness gates and a tightly controlled Day-1 scope.
80%
custom orders with
margin erosion
5
operating locations
across US & Canada
12
month target
for go-live
Decision priorities
1
Protect continuity
2
Stabilize BOM + labor data
3
Deliver margin transparency
4
Defer non-critical complexity
Notes: Emphasize the recommendation: one core operating backbone for Day 1, not an attempt to transform every function at once.

## Slide 3
Current-state diagnosis
Fragmented applications create unreliable product data, weak costing and operational delays.
03
⚙
Engineering DB
BOMs + ECNs
ERP
Legacy ERP
Finance • MRP • Procurement
Cloud CRM
unintegrated
HRIS / Payroll
siloed
Excel
shadow reporting
Fragile nightly sync
Operational impact
BOM failures drive delays, rework and expedited costs.
Financial impact
Unreliable labor capture prevents trusted margin reporting.
Management impact
Executives lack a single reliable contribution-margin view.
Notes: Explain that the real problem is not just “old ERP”; it is disconnected data causing business consequences.

## Slide 4
Business objectives
Measure the program by operational control and margin visibility, not just system launch.
04
🛡
Protect continuity
Keep all five locations able to buy, build, ship, invoice and close during transition.
🔧
Govern product data
Create one controlled flow for items, BOMs, revisions and ECNs.
$
Improve margin visibility
Capture material, labor, rework and order cost to compare estimate vs. actual.
✓
Standardize critical processes
Reduce uncontrolled spreadsheet workarounds while preserving necessary local controls.
Executive lens: prioritize requirements that protect continuity, regulatory/financial control, and margin transparency.
Notes: Use this slide to remind reviewers that every scope decision is judged against these objectives.

## Slide 5
Implementation approach
A phased program with formal stage gates and one coherent core production release.
05
Program design principle
Design and test the tightly connected operating chain together: order → engineering/BOM → procurement → inventory → manufacturing → finance.
1
Mobilize
Charter, governance, plan
M1
2
Discover & design
Fit-to-standard workshops
M2–3
3
Build
Configure, integrations, data cleanse
M4–6
4
Test & train
SIT, UAT, migration rehearsals
M7–10
5
Cutover
Mock close, go-live, hypercare
M11–12
Gate rule: no phase exits solely because the calendar date arrived — each gate requires evidence of process, data, people and control readiness.
Notes: State that location waves should be confirmed during discovery based on site readiness, shared inventory and intercompany complexity.

## Slide 6
Scope and sequencing
Include the minimum complete operating backbone at Day 1; defer complexity that can safely wait.
06
Day-1 must-haves
Deliberately deferred
Finance, multi-entity accounting and close
Order management through invoicing
Item, BOM revision and ECN control
Procurement, inventory and manufacturing
Labor capture and essential margin reporting
Security, approvals and audit controls
Full CRM replacement
Broad HR / payroll transformation
All 20+ years of legacy transactions
Low-value custom reports and dashboards
Non-critical automations and cosmetic enhancements
Unproven advanced analytics or AI features
Include when it protects operations, compliance or near-term margin visibility
Defer when a safe workaround exists and Day-1 risk exceeds Day-1 value
Notes: This is the slide most likely to be challenged. Defend scope by tying every inclusion/deferment to business continuity and risk.

## Slide 7
Data and historical access strategy
Preserve uninterrupted access without loading every legacy transaction into the new ERP.
07
Recommended treatment by data type
Migrate fully
Active masters, approved BOMs, open orders, AR/AP, inventory, GL opening balances.
Migrate selectively
Recent comparative financial, customer, supplier and profitability history where value justifies effort.
Archive
Older closed transactions, obsolete records and superseded revisions in secure read-only access.
Extract
Legacy ERP + Engineering DB
Cleanse
Duplicates, units, revisions
Load
ERP + reporting archive
Reconcile
Business owner sign-off
Key decision: business owners, not IT alone, approve whether data is correct and fit for go-live.
Notes: Clarify that uninterrupted access is satisfied by a secure archive plus selected migration. This reduces cost and migration risk.

## Slide 8
Reporting and month-end continuity
Do not go live until executives and Finance can trust the numbers.
08
Before go-live
KPI catalogue
Legacy report snapshots
Mock close rehearsal
During cutover
Freeze rules
Opening balances
Subledger reconciliation
After go-live
New ERP current reporting
Archive historical drill-down
First-close support
Governed KPI definition: contribution margin must use agreed treatment of material, labor, subcontracting, freight, rework and overhead.
Notes: Tell reviewers the month-end close is a business-critical test. The first close should not be discovered after go-live.

## Slide 9
Top risks and mitigations
Focus executive attention on the few risks that can materially harm continuity or trust.
09
1
Operational disruption at go-live
Mock cutovers, go/no-go criteria, fallback points, hypercare roster
2
Poor BOM / master data quality
Data owners, cleansing, migration rehearsals, Engineering + Operations sign-off
3
Scope creep and over-customization
Fit-to-standard rules, change-control board, post-go-live backlog
4
User adoption failure
Super-user network, role-based training, practice scenarios, adoption metrics
5
Reporting / first-close failure
KPI catalogue, reconciliations, mock close, dedicated Finance support
Risk ownership must sit with named business leaders; IT can coordinate but cannot approve business data or process readiness alone.
Notes: When asked for the biggest risk, identify BOM/master-data quality or go-live disruption and explain why.

## Slide 10
Governance and decision rights
Run the project as enterprise transformation, not an IT-only software deployment.
10
Executive Sponsor
Owns outcomes; removes barriers
Steering Committee
Approves scope, budget, policy and go-live
Program Manager
Integrated plan, RAID, dependencies, readiness evidence
Process Owners + Data Owners + Super Users
Design, test, approve data, train and support adoption
Stage gates
Design approval
Build complete
SIT exit
UAT exit
Go-live authorization
Decision rule
Major changes to scope, budget or timeline require documented impact analysis and Steering Committee approval.
Notes: Governance is about who can make decisions. This prevents every department from expanding scope independently.

## Slide 11
Success measures and next executive actions
Baseline performance now; hold the program accountable for business outcomes after go-live.
11
✓
BOM reliability
Critical sync / release failures reduced
✓
Labor capture
High compliance with time entry by role
✓
Margin visibility
Order contribution margin available and trusted
✓
Close continuity
First live close completed with reconciled subledgers
✓
Adoption
Users trained; spreadsheet workarounds reduced
✓
Operations
Production delays and expedite costs trending down
Immediate executive actions
Confirm sponsor and Steering Committee • Approve Day-1 scope principles • Appoint process and data owners • Protect SME capacity • Authorize Month 1 discovery and baseline measurement
Notes: Close by asking for executive alignment on governance, scope principles and dedicated business resources.